## Advanced Critical Path Analysis
AnalystLab Africa Consulting
Advanced Critical Path Analysis
Project: AI-Powered Customer Churn Prediction & Retention System: Tarrose Retail
Method: forward/backward-pass CPM built directly on the Project Schedule's real dependency graph (incl. the two phase-gate checkpoints and every FS/SS link), in working days. Start-to-Start edges honor their actual overlap (e.g. 7.4->8.1 = SS+3 days); Finish-to-Start edges use a minimal 0-day lag, so any larger gap between a predecessor's finish and its successor's start shows up as genuine float rather than being hidden. Early Start/Finish below reproduce the Project Schedule's Start/Finish exactly.
Activity ID | Activity Name | Duration (Working Days) | Predecessor (Type) | Early Start (= Baseline Start) | Early Finish (= Baseline Finish) | Late Start | Late Finish | Float (Working Days) | Status
1.1 | Project Charter | 1 | Start | 2026-08-10 | 2026-08-10 | 2026-09-21 | 2026-09-21 | 30 | Non-Critical
1.2 | Business Case | 2 | 1.1 (SS) | 2026-08-10 | 2026-08-11 | 2026-09-21 | 2026-09-22 | 30 | Non-Critical
1.3 | Stakeholder Requirements | 2 | 1.2 (FS) | 2026-08-11 | 2026-08-12 | 2026-09-22 | 2026-09-23 | 30 | Non-Critical
1.4 | Project Objectives | 2 | 1.3 (FS) | 2026-08-13 | 2026-08-14 | 2026-12-22 | 2026-12-23 | 93 | Non-Critical
2.1 | Scope Baseline | 3 | 1.3 (FS) | 2026-08-12 | 2026-08-14 | 2026-09-23 | 2026-09-25 | 30 | Non-Critical
2.2 | Project Schedule | 2 | 2.1 (FS) | 2026-08-17 | 2026-08-18 | 2026-09-25 | 2026-09-28 | 29 | Non-Critical
2.3 | Resource Plan | 3 | 2.2 (SS) | 2026-08-17 | 2026-08-19 | 2026-09-25 | 2026-09-29 | 29 | Non-Critical
2.4 | Risk Plan | 3 | 2.2 (FS) | 2026-08-18 | 2026-08-20 | 2026-09-29 | 2026-10-01 | 30 | Non-Critical
2.5 | Communication Plan | 3 | 2.3 (FS) | 2026-08-19 | 2026-08-21 | 2026-09-29 | 2026-10-01 | 29 | Non-Critical
2.6 | Data Governance Plan | 3 | 2.5 (SS) | 2026-08-19 | 2026-08-21 | 2026-09-29 | 2026-10-01 | 29 | Non-Critical
3.1 | POS Data Assessment | 3 | 2.0 gate (FS) | 2026-08-24 | 2026-08-26 | 2026-10-01 | 2026-10-05 | 28 | Non-Critical
3.2 | E-commerce Data Assessment | 3 | 3.1 (FS) | 2026-08-26 | 2026-08-28 | 2026-10-05 | 2026-10-07 | 28 | Non-Critical
3.3 | Loyalty Data Assessment | 3 | 3.2 (FS) | 2026-08-31 | 2026-09-02 | 2026-10-07 | 2026-10-09 | 27 | Non-Critical
3.4 | Customer Identity Resolution | 6 | 3.3 (FS) | 2026-09-02 | 2026-09-09 | 2026-10-09 | 2026-10-16 | 27 | Non-Critical
3.5 | Data Integration Pipeline | 6 | 3.4 (FS) | 2026-09-09 | 2026-09-16 | 2026-10-16 | 2026-10-23 | 27 | Non-Critical
3.6 | Data Quality Validation | 5 | 3.5 (SS+3d) | 2026-09-14 | 2026-09-18 | 2026-10-21 | 2026-10-27 | 27 | Non-Critical
4.1 | Churn Definition | 3 | 3.0 gate (FS) | 2026-09-21 | 2026-09-23 | 2026-10-27 | 2026-10-29 | 26 | Non-Critical
4.2 | Feature Engineering | 8 | 4.1 (FS) | 2026-09-23 | 2026-10-02 | 2026-10-29 | 2026-11-09 | 26 | Non-Critical
4.3 | Model Development | 11 | 4.2 (FS) | 2026-10-02 | 2026-10-16 | 2026-11-09 | 2026-11-23 | 26 | Non-Critical
4.4 | Model Validation | 6 | 4.3 (FS) | 2026-10-16 | 2026-10-23 | 2026-11-23 | 2026-11-30 | 26 | Non-Critical
4.5 | Model Explainability | 3 | 4.4 (SS+3d) | 2026-10-21 | 2026-10-23 | 2026-11-26 | 2026-11-30 | 26 | Non-Critical
4.6 | Model Approval | 3 | 4.4, 4.5 (FS) | 2026-10-26 | 2026-10-28 | 2026-11-30 | 2026-12-02 | 25 | Non-Critical
5.1 | Dashboard Requirements | 3 | 4.2 (FS) | 2026-10-12 | 2026-10-14 | 2026-11-23 | 2026-11-25 | 30 | Non-Critical
5.2 | Dashboard Design | 6 | 5.1 (FS) | 2026-10-14 | 2026-10-21 | 2026-11-25 | 2026-12-02 | 30 | Non-Critical
5.3 | Dashboard Development | 13 | 5.2 (FS) | 2026-10-21 | 2026-11-06 | 2026-12-02 | 2026-12-18 | 30 | Non-Critical
5.4 | User Acceptance Testing | 3 | 5.3 (SS+10d) | 2026-11-04 | 2026-11-06 | 2026-12-16 | 2026-12-18 | 30 | Non-Critical
5.5 | User Training | 4 | 5.4 (FS) | 2026-11-06 | 2026-11-11 | 2026-12-18 | 2026-12-23 | 30 | Non-Critical
6.1 | Customer Segmentation | 3 | 4.3 (FS) | 2026-10-19 | 2026-10-21 | 2026-12-01 | 2026-12-03 | 31 | Non-Critical
6.2 | Retention Intervention Design | 3 | 6.1 (FS) | 2026-10-26 | 2026-10-28 | 2026-12-03 | 2026-12-07 | 28 | Non-Critical
6.3 | Control Group | 3 | 6.2 (FS) | 2026-11-02 | 2026-11-04 | 2026-12-07 | 2026-12-09 | 25 | Non-Critical
6.4 | Pilot Launch | 3 | 6.3 (FS) | 2026-11-09 | 2026-11-11 | 2026-12-09 | 2026-12-11 | 22 | Non-Critical
6.5 | Pilot Evaluation | 3 | 6.4 (FS) | 2026-12-02 | 2026-12-04 | 2026-12-11 | 2026-12-15 | 7 | Non-Critical
7.1 | Production Deployment | 8 | 4.6 (FS) | 2026-11-30 | 2026-12-09 | 2026-12-02 | 2026-12-11 | 2 | Near-Critical
7.2 | Monitoring Process | 3 | 7.1 (SS+5d) | 2026-12-07 | 2026-12-09 | 2026-12-09 | 2026-12-11 | 2 | Near-Critical
7.3 | Retraining Process | 3 | 7.2 (FS) | 2026-12-09 | 2026-12-11 | 2026-12-11 | 2026-12-15 | 2 | Near-Critical
7.4 | Operational Handover | 5 | 7.3, 6.5 (FS) | 2026-12-14 | 2026-12-18 | 2026-12-15 | 2026-12-21 | 1 | Near-Critical
8.1 | Final Evaluation | 2 | 7.4 (SS+3d) | 2026-12-17 | 2026-12-18 | 2026-12-18 | 2026-12-21 | 1 | Near-Critical
8.2 | Lessons Learned | 2 | 8.1 (FS) | 2026-12-21 | 2026-12-22 | 2026-12-21 | 2026-12-22 | 0 | CRITICAL
8.3 | Final Documentation | 2 | 8.2 (FS) | 2026-12-22 | 2026-12-23 | 2026-12-22 | 2026-12-23 | 0 | CRITICAL
8.4 | Sign-off | 1 | 8.3 (FS) | 2026-12-23 | 2026-12-23 | 2026-12-23 | 2026-12-23 | 0 | CRITICAL
Summary
Total activities analysed: |  |  | 40 (+2 phase-gate checkpoints: 2.0, 3.0)
Critical activities (zero float): |  |  | 3 — Lessons Learned (8.2), Final Documentation (8.3), Sign-off (8.4)
Near-critical activities (1–2 working days float): |  |  | 5 — Production Deployment (7.1), Monitoring Process (7.2), Retraining Process (7.3), Operational Handover (7.4), Final Evaluation (8.1)
Project duration (matches Project Schedule exactly): |  |  | 10-Aug-2026 → 23-Dec-2026
1. The Critical Path
1.1 → 1.2 → 1.3 → 2.1 → 2.2 → 2.3 → 2.5 → 2.6 → [2.0 Gate] → 3.1 → 3.2 → 3.3 → 3.4 → 3.5 → 3.6 → [3.0 Gate] → 4.1 → 4.2 → 4.3 → 4.4 → 4.5 → 4.6 → 7.1 → 7.2 → 7.3 → 7.4 → 8.1 → 8.2 → 8.3 → 8.4
Only the final three activities — Lessons Learned (8.2), Final Documentation (8.3), and Sign-off (8.4) — carry zero float and are formally CRITICAL. Production Deployment through Final Evaluation (7.1–7.4, 8.1) are Near-Critical with 1–2 days of float, and are treated as part of the practical critical chain because that little float can be consumed by a single short delay.
2. Total Project Duration
10-Aug-2026 → 23-Dec-2026 (95 working days / ~19.3 calendar weeks), matching the Project Schedule baseline exactly.
3. Activities With Scheduling Flexibility
Phases 1.0–6.0 carry substantial float and can absorb delay without moving the finish date: Retention Pilot (6.1–6.4, 22–31 days), the Dashboard branch (5.1–5.5, 30 days), the Data Integration and Model Development chains (3.1–4.6, 25–30 days), and Project Objectives (1.4, 93 days — see the modelling note in the Notes section below). Pilot Evaluation (6.5) is the tightest of the flexible activities at 7 days float, since it feeds directly into the near-critical Operational Handover (7.4).
4. Why the Critical Path Matters
The critical path is the chain of activities with no scheduling slack — it sets the shortest possible time in which the project can finish, and it tells the Project Manager exactly where schedule attention has to go. Every hour spent expediting a flexible activity (e.g. the Dashboard, 30 days of float) has no effect on the finish date, while the same hour spent on a critical or near-critical activity (7.1–8.4) directly moves 23-Dec-2026. Knowing the critical path is what lets a Sponsor make an informed trade-off — approve extra resource on a critical activity, or accept a schedule impact — instead of guessing.
5. Impact of Delays on Critical Activities
A delay to Lessons Learned, Final Documentation, or Sign-off (8.2–8.4) pushes the project finish date back day-for-day, with no buffer. The near-critical band immediately ahead of them — Production Deployment, Monitoring Process, Retraining Process, Operational Handover, and Final Evaluation (7.1–7.4, 8.1) — has only 1–2 working days of float each, so even a small delay there will also push the finish date out. Because the front two-thirds of the project (Phases 1.0–6.0) carry 25+ working days of float each — the direct result of the schedule's fast-tracked (Start-to-Start) overlaps being honored while ordinary sequential gaps are correctly left open as float — a modest slip earlier in the schedule is unlikely to threaten the 23-Dec-2026 date on its own. But it steadily erodes the buffer protecting the back-end chain, and the festive-season closure (Weeks 19–20) sits directly against that chain with almost no room left to absorb further slippage.
Notes & Modelling Assumptions
• Start-to-Start lags (e.g. 7.4→8.1 = 3 days, 7.1→7.2 = 5 days) are treated as genuine, deliberate overlaps and honored exactly; ordinary Finish-to-Start gaps (e.g. the 23-day gap between Model Approval and Production Deployment) are treated as available float, not a hard requirement. See the Schedule Risk Assessment for the implication if that assumption doesn't hold.
• 1.4 Project Objectives shows 93 days of float because no downstream activity in the current network formally depends on it finishing — in practice its accuracy/churn-reduction targets should still be re-confirmed at the 4.6 Model Approval gate.
• 2.0 and 3.0 phase-gate checkpoints require every activity in that phase to finish before the next phase can begin — this is why 3.1 and 4.1 cannot start until the slowest activity in the prior phase completes.
Legend: pink = Critical (0 days float) · yellow = Near-Critical (1–2 days float)