## Schedule Risk Assessment
AnalystLab Africa Consulting
Schedule Risk Assessment
Project: AI-Powered Customer Churn Prediction & Retention System : Tarrose Retail
Risks specific to schedule adherence, cross-referenced to the Advanced Critical Path Analysis and Week 1 Risk Register where relevant.
Risk ID | Risk Description | Probability | Potential Impact | Affected Activity / Project Area | Mitigation Strategy | Contingency Plan
SR-01 | Dependency delay: the 2.0 and 3.0 phase-gate checkpoints require every activity in the phase to finish before the next phase can start, so a single slow task inside a gated phase delays every downstream activity. | Medium | High | 3.0 Integrated Customer Data gate; cascades into all of Phase 4.0–8.0 | Track all gate-feeding activities individually in the weekly schedule review, not just the phase as a whole, so a lagging activity is caught before it reaches the gate date. | If a gate activity slips, pull float from a non-critical branch (e.g. reassign Data Engineer time freed from the Dashboard track) to recover the specific lagging task rather than delaying the whole gate.
SR-02 | Resource unavailability: the Data Scientist is the sole named resource for Model Development (4.3, 11 working days) and Model Validation (4.4) — both on the critical/near-critical chain — with no named backup. | Medium | High | 4.3 Model Development, 4.4 Model Validation (0 days float) | Confirm the Data Scientist's availability at each weekly check-in through Weeks 7–18; flag any competing engagement immediately to the Project Manager rather than at the point of conflict. | Pre-identify a contract data scientist or AnalystLab colleague who could be onboarded within 3 working days if the primary resource becomes unavailable.
SR-03 | Delayed approvals: Model Approval (4.6) and the production readiness Compliance sign-off (within 7.1) both require Sponsor or Compliance Officer availability, which is outside the Project Manager's direct control. | Medium | Medium | 4.6 Model Approval; 7.1 Production Deployment (Compliance sign-off) | Schedule Sponsor and Compliance Officer calendar holds for phase-gate reviews at the start of the project, not ad hoc, so approval slots are reserved in advance. | If an approval is delayed beyond 2 working days, escalate directly to the Sponsor for an interim conditional approval so downstream work can begin at risk, pending final sign-off.
SR-04 | Technology/system failure: POS, e-commerce, and loyalty source systems (feeding 3.1–3.3) are Tarrose Retail's own production systems, not AnalystLab-controlled, and a system change or outage could invalidate an in-progress data assessment. | Low | High | 3.1–3.3 Data Assessment activities; cascades through the full Phase 3.0–8.0 chain | Confirm with the IT Lead that no planned system changes, migrations, or maintenance windows fall within Weeks 3–6 before data assessment work begins. | If a source system changes mid-assessment, re-scope the affected assessment activity only (not the full phase) and absorb the delay using Phase 3.0's own float before it reaches the 3.0 gate.
SR-05 | Scope change: a change to the 75% model accuracy target or churn-reduction success criteria after Model Development has started would require rework of 4.3–4.4, both on the near-zero-float chain. | Low | High | 4.3 Model Development, 4.4 Model Validation, 4.6 Model Approval | Enforce the Charter's existing change-control rule: any change affecting the 75% accuracy target requires formal Sponsor sign-off before it is actioned, preventing informal scope drift. | If a target change is approved, re-run the Critical Path Analysis immediately to quantify the schedule impact before committing to a revised delivery date.
SR-06 | Communication breakdown: the Retention Pilot (6.0) and Dashboard (5.0) branches both depend on Marketing & Customer Service Team availability, which is described in the Charter as 'light involvement' — a missed handoff could stall both branches simultaneously. | Medium | Low | 5.4–5.5 User Acceptance Testing / Training; 6.2–6.4 Retention Intervention Design through Pilot Launch | Confirm the Marketing & Customer Service Team's specific availability windows for Weeks 11–17 in writing during Phase 2.0 resource planning, rather than assuming general availability. | Because both branches carry 20+ days of float, absorb a short delay within the existing buffer; only escalate to the Sponsor if the delay would consume more than half of the available float.
SR-07 | Delay in task completion: Production Deployment (7.1, 8 working days) is the longest single activity in the near-critical band and has historically been where technical deployment issues surface on similar projects. | Medium | High | 7.1 Production Deployment (2 days float); cascades into 7.2–8.4 | Run a deployment dry-run in a staging environment during Week 17, before the scheduled production deployment window, to surface issues while float still exists in Phase 4.0. | Hold the IT Lead's Week 19 allocation (already increased to ~50% per the Resource Plan) as a dedicated recovery buffer if deployment runs past its 8-day estimate.
Legend: pink = High impact · yellow = Medium impact · green = Low impact