## Sheet1
AnalystLab Africa Consulting
Communication Plan
Project: AI- Powered Customer Churn Prediction & Retention System - Tarrose Retail
Team members | Information | Frequency | Method | Owner
Project Sponsor (Head of Marketing & CX) | Overall project status, budget, key decisions, risk escalations | Weekly | Status report email + monthly steering meeting | Project Manager
IT / Data Engineering Team | Technical requirements, data integration progress, blockers | Daily/Weekly | Stand-up meetings, project chat channel | Project Manager
Data Scientist | Model development progress, feature engineering decisions, validation/accuracy results, retraining process design | Weekly | Working sessions, project chat channel | Project Manager
Marketing & Customer Service Teams | Dashboard design updates, training schedule, segmentation logic | Bi-weekly | Working sessions, email updates | Project Manager
Loyalty Programme Manager | Data quality checkpoints, customer identifier consistency, impact on model accuract | Bi-weekly | Working sessions, email updates | Project Manager
Compliance Officer | Data handling approach, POPIA compliance checkpoints | At each compliance milestone | Formal sign-off documents, review meetings | Project Manager
Finance Manager | Budget vs. actual spend, forecast to completion | Monthly | Budget report email | Project Manager
AnalystLab Delivery Team (Internal) | Task progress, technical issues, resourcing needs | Daily | Internal stand-up, project management tool - Asana | Project Manager
All Stakeholders | Major milestones, phase completions, go/no-go decisions | At each phase gate | Milestone summary email | Project Manager