## Risk Register
AnalystLab Africa Consulting | [7 empty] | Level | Score
RISK REGISTER | [7 empty] | Low | 1
Project: AI-Powered Customer Churn Prediction & Retention System - Tarrose Retail | [7 empty] | Medium | 2
[8 empty] | High | 3
ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation Strategy | Owner
R1 | Data integration complexity across POS, e-commerce, and loyalty platforms delays project timeline | Technical | High | High | 9 | Conduct early data source audit (Phase 3.1); allocate buffer time; involve IT team from project start | IT Lead
R2 | Inconsistent or missing customer identifiers across systems reduce data matching accuracy | Data Quality | High | High | 9 | Define a common ID standard early; run data quality checks before model build begins | Data Engineer
R3 | Churn prediction model fails to reach the 75% accuracy target | Technical | Medium | High | 6 | Use iterative testing cycles; adjust features/approach; set a realistic accuracy checkpoint before pilot | Data Scientist
R4 | Marketing and Customer Service teams under-adopt or ignore at-risk customer flags | Organisational | Medium | High | 6 | Involve teams in dashboard design; provide hands-on training; assign a champion in each team | Project Manager
R5 | Non-compliance with POPIA in handling customer data | Compliance | Low | High | 3 | Compliance Officer sign-off required before data integration; build in a formal privacy review checkpoint | Compliance Officer
R6 | Legacy POS system has limited or no API access, blocking data extraction | Technical | Medium | High | 6 | Assess POS access in Week 3 audit; have a manual export fallback plan ready | IT Lead
R7 | Project exceeds the approved R1 000 000 budget | Financial | Medium | Medium | 4 | Monthly budget tracking against plan; sponsor sign-off required for any scope changes | Project Manager
R8 | Pilot retention campaign results are inconclusive due to small flagged-customer sample size | Analytical | Medium | Medium | 4 | Set a minimum sample size threshold before launch; extend pilot window if needed | Data Scientist
R9 | Key project team member (e.g., data engineer) becomes unavailable mid-project | Resourcing | Low | Medium | 2 | Document data pipeline work as it's built; identify a backup resource early | Project Manager
R10 | Scope creep - client requests product analytics features mid-project | Scope | Medium | Medium | 4 | Reinforce agreed scope in Charter; route new requests through formal change control | Project Manager
R11 | Insufficient internal capacity at Tarrose Retail to sustain monitoring and retraining after handover | Operational/Handover | Medium | High | 6 | Confirm internal team capacity with Tarrose Retail management in Weeks 1–2; onboard internal IT/Data team early (WBS 7.4); make Sponsor's full-rollout decision conditional on demonstrated readiness | Project Manager
R12 | Schedule pressure from the festive-season office closure falling within Weeks 19–20 | Schedule | Medium | Medium | 4 | Sequence final handover and closure activities (WBS 7.4, 8.0) to complete key milestones before the closure window; confirm availability of key stakeholders for sign-off | Project Manager
Note: Risk Score = Likelihood score (1–3) × Impact score (1–3). Score ≥6 = High priority, 3–4 = Medium, ≤2 = Low.