## Sheet1
AnalystLab Africa Consulting
STAKEHOLDER REGISTER
Project: AI- Powered Customer Churn Prediction & Retention System - Tarrose Retail
Stakeholder | Interest in Project | Influence | Impact | Engagement Strategy | Power/ Interest Quadrant
Head of Marketing & Customer (Sponsor) | Owns the churn/retention outcome; needs actionable at-risk customer lists to justify ROI | High | High | Manage Closely | High Power/ High Interest
IT/ Data Engineering Team | Responsible for integrating POS, e-commerce, and loyalty data sources | High | High | Manage Closely | High Power/ High Interest
Data Scientist | Builds, validates, and documents the churn prediction model and retraining process; model accuracy directly drives project success | High | High | Manage Closely | High Power/ High Interest
Customer Service Manager | Will use at-risk flags to prioritise retention outreach and support calls | Medium | High | Keep Informed | Medium Power/ High Interest
Marketing Team | Executes retention campaigns based on segmentation and churn scores | Medium | High | Keep Informed | Medium Power/ High Interest
Compliance Officer | Ensures customer data use complies with POPIA | High | Medium | Keep Informed | High Power/ Medium Interest
Loyalty Programme Manager | Loyalty data quality and customer ID consistency directly affects model accuracy | Medium | Medium | Keep Informed | Medium Power/ Medium Interest
Store Operations Manager | Indirectly affected if retention offers require in-store redemption support | Low | Medium | Monitor | Low Power/ Medium Interest
Finance Manager | Approves and monitors the R1 000 000 project budget | Medium | Medium | Keep informed | Medium Power/ Medium Interest
AnalystLab Africa Consulting (Delivery Team) | Responsible for on-time, on-budget delivery of the project | High | High | Manage Closely | High Power/ High Interest
Tarrose Retail Customers (End Beneficiaries) | Recipients of retention offers; data privacy and relevance of offers affects trust | Low | High | Should be keep Informed | Low Power/ High Interest
Note: Power = stakeholder's influence over project decisions. Interest = how much the project outcome affects the stakeholder. Engagement strategy follows the standard Power/Interest grid (Manage Closely, Keep Satisfied, Keep Informed, Monitor