## WBS
AnalystLab Africa Consulting
Work Breakdown Structure
Tarrose Retail Churn Pediction & Retention System
Code | Task Name | Description | Start Date | End Date | Owner | Notes
1.0 | Approved Project Foundation | Foundational documents that establish and authorise the project. | 2026-08-10 | 2026-08-14 | (Project Manager) | Phase gate: Sponsor sign-off to proceed to planning.
1.1 | Project Charter | Draft and approve the project charter defining purpose, scope and authority. | 2026-08-10 | 2026-08-10 | (Project Manager) | Baseline document; approved 09 Aug 2026.
1.2 | Business Case | Document the rationale, expected benefits and value of the churn prediction system. | 2026-08-10 | 2026-08-11 | (Project Manager)
1.3 | Stakeholder Requirements | Capture requirements from Marketing, Customer Service, IT, Data and Compliance stakeholders. | 2026-08-11 | 2026-08-12 | (Project Manager)
1.4 | Project Objectives | Define measurable objectives aligned to the 75% accuracy and 10% churn-reduction targets. | 2026-08-13 | 2026-08-14 | (Project Manager)
2.0 | Approved Project Plan | Baseline planning documents covering scope, schedule, resources, risk, communication and governance. | 2026-08-10 | 2026-08-21 | (Project Manager) | Phase gate: Sponsor approval of baseline before data work begins.
2.1 | Scope Baseline | Finalise in-scope / out-of-scope statement and WBS baseline. | 2026-08-12 | 2026-08-14 | (Project Manager)
2.2 | Project Schedule | Build the 20-week integrated project schedule. | 2026-08-17 | 2026-08-18 | (Project Manager)
2.3 | Resource Plan | Confirm resource allocation acs Data Engineer, Data Scientist, IT Lead, Compliance and Marketing. | 2026-08-17 | 2026-08-19 | (Project Manager)
2.4 | Risk Plan | Develop the expanded risk register given data integration and POPIA exposure. | 2026-08-18 | 2026-08-20 | (Project Manager)
2.5 | Communication Plan | Document reporting cadence and stakeholder communication channels. | 2026-08-19 | 2026-08-21 | (Project Manager)
2.6 | Data Governance Plan | Define POPIA-compliant data handling rules for production and monitoring. | 2026-08-19 | 2026-08-21 | Compliance Officer
3.0 | Integrated Customer Data | Unify POS, e-commerce and loyalty data into a single customer view. | 2026-08-24 | 2026-09-18 | Data Engineer | Depends on identifier confirmation with IT Lead (Weeks 1-2).
3.1 | POS Data Assessment | Assess POS data structure, quality and availability. | 2026-08-24 | 2026-08-26 | Data Engineer
3.2 | E-commerce Data Assessment | Assess e-commerce platform data structure, quality and availability. | 2026-08-26 | 2026-08-28 | Data Engineer
3.3 | Loyalty Data Assessment | Assess loyalty programme data structure, quality and availability. | 2026-08-31 | 2026-09-02 | Data Engineer
3.4 | Customer Identity Resolution | Establish or create a common customer identifier acs all three source systems. | 2026-09-02 | 2026-09-09 | Data Engineer | Key risk: inconsistent identifiers between systems.
3.5 | Data Integration Pipeline | Build the pipeline that unifies POS, e-commerce and loyalty data. | 2026-09-09 | 2026-09-16 | Data Engineer
3.6 | Data Quality Validation | Validate completeness, accuracy and consistency of the unified dataset. | 2026-09-14 | 2026-09-18 | Data Engineer
4.0 | Churn Prediction Solution | Develop, test and approve the churn prediction model. | 2026-09-21 | 2026-10-30 | Data Scientist | Hybrid work package: short iterative test cycles within the predictive plan.
4.1 | Churn Definition | Define what constitutes 'churn' for a loyalty-programme customer. | 2026-09-21 | 2026-09-23 | Data Scientist
4.2 | Feature Engineering | Engineer behavioural and transactional features from the unified dataset. | 2026-09-23 | 2026-10-02 | Data Scientist
4.3 | Model Development | Iteratively build and tune candidate churn prediction models. | 2026-10-02 | 2026-10-16 | Data Scientist | Iterative testing cycles (hybrid approach).
4.4 | Model Validation | Test model against held-out data; confirm progress toward 75% accuracy target. | 2026-10-16 | 2026-10-23 | Data Scientist
4.5 | Model Explainability | Document how the model produces churn scores for business stakeholder trust. | 2026-10-21 | 2026-10-23 | Data Scientist
4.6 | Model Approval | Present model results for approval to proceed to dashboard build and pilot. | 2026-10-26 | 2026-10-28 | Sponsor (Head of Marketing & CX) | Phase gate: Sponsor sign-off required (affects accuracy target).
5.0 | Customer Intelligence Dashboard | Build the at-risk customer reporting dashboard for Marketing and Customer Service. | 2026-10-12 | 2026-11-13 | IT Lead
5.1 | Dashboard Requirements | Confirm dashboard requirements with Marketing & Customer Service. | 2026-10-12 | 2026-10-14 | IT Lead
5.2 | Dashboard Design | Design dashboard layout, segmentation views and churn score reporting. | 2026-10-14 | 2026-10-21 | IT Lead
5.3 | Dashboard Development | Build the dashboard against the validated churn model outputs. | 2026-10-21 | 2026-11-06 | IT Lead
5.4 | User Acceptance Testing | Marketing & Customer Service test the dashboard against requirements. | 2026-11-04 | 2026-11-06 | Marketing & Customer Service Team
5.5 | User Training | Train Marketing & Customer Service teams to use the dashboard outputs. | 2026-11-06 | 2026-11-11 | Marketing & Customer Service Team
6.0 | Retention Pilot | Run and evaluate a pilot retention campaign on flagged at-risk customers. | 2026-10-19 | 2026-12-04 | Marketing & Customer Service Team | Success threshold: 10% churn reduction vs control group.
6.1 | Customer Segmentation | Layer behavioural segmentation (frequency, spend, category) on churn scores. | 2026-10-19 | 2026-10-21 | Data Scientist
6.2 | Retention Intervention Design | Design retention actions/offers for each flagged segment. | 2026-10-26 | 2026-10-28 | Marketing & Customer Service Team
6.3 | Control Group | Define a control group of at-risk customers to measure the pilot against. | 2026-11-02 | 2026-11-04 | Data Scientist
6.4 | Pilot Launch | Launch retention interventions to the flagged segment. | 2026-11-09 | 2026-11-11 | Marketing & Customer Service Team
6.5 | Pilot Evaluation | Measure churn rate in the flagged segment against the control group. | 2026-12-02 | 2026-12-04 | Data Scientist | Feeds into the full-rollout decision.
7.0 | Operationalised Solution | Deploy the model and dashboard to production with monitoring, retraining and handover. | 2026-11-30 | 2026-12-18 | IT Lead | Own phase-gate sign-off before full rollout.
7.1 | Production Deployment | Deploy the churn model and dashboard into Tarrose Retail's production environment. | 2026-11-30 | 2026-12-09 | IT Lead | Compliance Officer sign-off required at production readiness gate.
7.2 | Monitoring Process | Set up ongoing monitoring of model performance and data quality. | 2026-12-07 | 2026-12-09 | IT Lead
7.3 | Retraining Process | Define and document the model retraining schedule and process. | 2026-12-09 | 2026-12-11 | Data Scientist
7.4 | Operational Handover | Formally hand over monitoring and retraining to Tarrose Retail's internal team. | 2026-12-14 | 2026-12-18 | Tarrose Retail Internal IT/Data Team | Phase gate: Sponsor decision on full rollout follows this handover.
8.0 | Project Closure | Close out the project and hand over final documentation. | 2026-12-15 | 2026-12-23 | (Project Manager) | Falls within the Weeks 19-20 festive-season office closure risk window.
8.1 | Final Evaluation | Evaluate delivery against the success criteria in the charter. | 2026-12-17 | 2026-12-18 | (Project Manager)
8.2 | Lessons Learned | Capture lessons learned for future AnalystLab Africa Consulting engagements. | 2026-12-21 | 2026-12-22 | (Project Manager)
8.3 | Final Documentation | Compile final project documentation and archive project records. | 2026-12-22 | 2026-12-23 | (Project Manager)
8.4 | Sign-off | Obtain formal Sponsor sign-off closing the project. | 2026-12-23 | 2026-12-23 | Sponsor (Head of Marketing & CX) | Final approval per Section 11 of the Project Charter.
Note: Kickoff is Mon 10-Aug-2026 (day after charter approval)