## Critical Path Analysis
Critical Path Analysis — AI-Powered Customer Churn Prediction & Retention System
Client: Tarrose Retail ¦ Prepared by: Rosely, Junior Project Manager, AnalystLab Africa Consulting
Activity ID | Activity Name | Duration (Working Days) | Predecessor (Type) | Early Start | Early Finish | Late Start | Late Finish | Float (Working Days) | Status
1.1 | Project Charter | 1 | Start | 10-Aug-26 | 10-Aug-26 | 10-Aug-26 | 10-Aug-26 | 0 | CRITICAL
1.2 | Business Case | 2 | 1.1 (SS) | 10-Aug-26 | 11-Aug-26 | 10-Aug-26 | 11-Aug-26 | 0 | CRITICAL
1.3 | Stakeholder Requirements | 2 | 1.2 (FS) | 11-Aug-26 | 12-Aug-26 | 11-Aug-26 | 12-Aug-26 | 0 | CRITICAL
1.4 | Project Objectives | 2 | 1.3 (FS) | 13-Aug-26 | 14-Aug-26 | 22-Dec-26 | 23-Dec-26 | 93 | Non-Critical
2.1 | Scope Baseline | 3 | 1.3 (FS) | 12-Aug-26 | 14-Aug-26 | 12-Aug-26 | 14-Aug-26 | 0 | CRITICAL
2.2 | Project Schedule | 2 | 2.1 (FS) | 17-Aug-26 | 18-Aug-26 | 17-Aug-26 | 18-Aug-26 | 0 | CRITICAL
2.3 | Resource Plan | 3 | 2.2 (SS) | 17-Aug-26 | 19-Aug-26 | 17-Aug-26 | 19-Aug-26 | 0 | CRITICAL
2.4 | Risk Plan | 3 | 2.2 (FS) | 18-Aug-26 | 20-Aug-26 | 18-Aug-26 | 20-Aug-26 | 0 | CRITICAL
2.5 | Communication Plan | 3 | 2.3 (FS) | 19-Aug-26 | 21-Aug-26 | 19-Aug-26 | 21-Aug-26 | 0 | CRITICAL
2.6 | Data Governance Plan | 3 | 2.5 (SS) | 19-Aug-26 | 21-Aug-26 | 19-Aug-26 | 21-Aug-26 | 0 | CRITICAL
3.1 | POS Data Assessment | 3 | 2.0 gate (FS) | 24-Aug-26 | 26-Aug-26 | 24-Aug-26 | 26-Aug-26 | 0 | CRITICAL
3.2 | E-commerce Data Assessment | 3 | 3.1 (FS) | 26-Aug-26 | 28-Aug-26 | 26-Aug-26 | 28-Aug-26 | 0 | CRITICAL
3.3 | Loyalty Data Assessment | 3 | 3.2 (FS) | 31-Aug-26 | 02-Sep-26 | 31-Aug-26 | 02-Sep-26 | 0 | CRITICAL
3.4 | Customer Identity Resolution | 6 | 3.3 (FS) | 02-Sep-26 | 09-Sep-26 | 02-Sep-26 | 09-Sep-26 | 0 | CRITICAL
3.5 | Data Integration Pipeline | 6 | 3.4 (FS) | 09-Sep-26 | 16-Sep-26 | 09-Sep-26 | 16-Sep-26 | 0 | CRITICAL
3.6 | Data Quality Validation | 5 | 3.5 (SS+3d) | 14-Sep-26 | 18-Sep-26 | 14-Sep-26 | 18-Sep-26 | 0 | CRITICAL
4.1 | Churn Definition | 3 | 3.0 gate (FS) | 21-Sep-26 | 23-Sep-26 | 21-Sep-26 | 23-Sep-26 | 0 | CRITICAL
4.2 | Feature Engineering | 8 | 4.1 (FS) | 23-Sep-26 | 02-Oct-26 | 23-Sep-26 | 02-Oct-26 | 0 | CRITICAL
4.3 | Model Development | 11 | 4.2 (FS) | 02-Oct-26 | 16-Oct-26 | 02-Oct-26 | 16-Oct-26 | 0 | CRITICAL
4.4 | Model Validation | 6 | 4.3 (FS) | 16-Oct-26 | 23-Oct-26 | 16-Oct-26 | 23-Oct-26 | 0 | CRITICAL
4.5 | Model Explainability | 3 | 4.4 (SS+lag) | 21-Oct-26 | 23-Oct-26 | 21-Oct-26 | 23-Oct-26 | 0 | CRITICAL
4.6 | Model Approval | 3 | 4.4, 4.5 (FS) | 26-Oct-26 | 28-Oct-26 | 26-Oct-26 | 28-Oct-26 | 0 | CRITICAL
5.1 | Dashboard Requirements | 3 | 4.2 (FS+lag) | 12-Oct-26 | 14-Oct-26 | 23-Nov-26 | 25-Nov-26 | 30 | Non-Critical
5.2 | Dashboard Design | 6 | 5.1 (FS) | 14-Oct-26 | 21-Oct-26 | 25-Nov-26 | 02-Dec-26 | 30 | Non-Critical
5.3 | Dashboard Development | 13 | 5.2 (FS) | 21-Oct-26 | 06-Nov-26 | 02-Dec-26 | 18-Dec-26 | 30 | Non-Critical
5.4 | User Acceptance Testing | 3 | 5.3 (SS+lag) | 04-Nov-26 | 06-Nov-26 | 16-Dec-26 | 18-Dec-26 | 30 | Non-Critical
5.5 | User Training | 4 | 5.4 (FS) | 06-Nov-26 | 11-Nov-26 | 18-Dec-26 | 23-Dec-26 | 30 | Non-Critical
6.1 | Customer Segmentation | 3 | 4.3 (FS) | 19-Oct-26 | 21-Oct-26 | 19-Oct-26 | 21-Oct-26 | 0 | CRITICAL
6.2 | Retention Intervention Design | 3 | 6.1 (FS+lag) | 26-Oct-26 | 28-Oct-26 | 26-Oct-26 | 28-Oct-26 | 0 | CRITICAL
6.3 | Control Group | 3 | 6.2 (FS+lag) | 02-Nov-26 | 04-Nov-26 | 02-Nov-26 | 04-Nov-26 | 0 | CRITICAL
6.4 | Pilot Launch | 3 | 6.3 (FS+lag) | 09-Nov-26 | 11-Nov-26 | 09-Nov-26 | 11-Nov-26 | 0 | CRITICAL
6.5 | Pilot Evaluation | 3 | 6.4 (FS+lag) | 02-Dec-26 | 04-Dec-26 | 02-Dec-26 | 04-Dec-26 | 0 | CRITICAL
7.1 | Production Deployment | 8 | 4.6 (FS+lag) | 30-Nov-26 | 09-Dec-26 | 30-Nov-26 | 09-Dec-26 | 0 | CRITICAL
7.2 | Monitoring Process | 3 | 7.1 (SS+lag) | 07-Dec-26 | 09-Dec-26 | 07-Dec-26 | 09-Dec-26 | 0 | CRITICAL
7.3 | Retraining Process | 3 | 7.2 (FS) | 09-Dec-26 | 11-Dec-26 | 09-Dec-26 | 11-Dec-26 | 0 | CRITICAL
7.4 | Operational Handover | 5 | 7.3, 6.5 (FS+lag) | 14-Dec-26 | 18-Dec-26 | 14-Dec-26 | 18-Dec-26 | 0 | CRITICAL
8.1 | Final Evaluation | 2 | 7.4 (SS+lag) | 17-Dec-26 | 18-Dec-26 | 17-Dec-26 | 18-Dec-26 | 0 | CRITICAL
8.2 | Lessons Learned | 2 | 8.1 (FS+lag) | 21-Dec-26 | 22-Dec-26 | 21-Dec-26 | 22-Dec-26 | 0 | CRITICAL
8.3 | Final Documentation | 2 | 8.2 (FS) | 22-Dec-26 | 23-Dec-26 | 22-Dec-26 | 23-Dec-26 | 0 | CRITICAL
8.4 | Sign-off | 1 | 8.3 (FS) | 23-Dec-26 | 23-Dec-26 | 23-Dec-26 | 23-Dec-26 | 0 | CRITICAL
Notes:
- Early Start/Early Finish are calculated forward from Project Start (10-Aug-2026), following the Predecessor/Type and lag stated in the Project Schedule.
- Late Start/Late Finish are calculated backward from Project Finish (23-Dec-2026), following the true successor chain for each activity (not a phase-level shortcut).
- Float = Late Start − Early Start (working days). Activities with 0 float are CRITICAL; all others are Non-Critical.
- Phase gate dependencies (e.g. 3.1 depends on the full 2.0 Approved Project Plan gate; 4.1 depends on the full 3.0 Integrated Customer Data gate) mean nearly all downstream activities inherit zero float, since a gate makes every feeding task as time-sensitive as its longest predecessor.
- Only Phase 5 (Customer Intelligence Dashboard, 30 days float) and 1.4 Project Objectives (93 days float) carry meaningful schedule buffer.