## Gantt Chart
AnalystLab Africa Consulting
Gantt Chart : AI-Powered Customer Churn Prediction & Retention System
Client: Tarrose Retail ¦ Red = Critical Path ¦ Green = Non-Critical (has float)
Code | Task Name | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
1.0 | Approved Project Foundation | bar: W1
1.1 | Project Charter | bar: W1
1.2 | Business Case | bar: W1
1.3 | Stakeholder Requirements | bar: W1
1.4 | Project Objectives | bar: W1
2.0 | Approved Project Plan | bar: W1 to W2
2.1 | Scope Baseline | bar: W1
2.2 | Project Schedule | bar: W2
2.3 | Resource Plan | bar: W2
2.4 | Risk Plan | bar: W2
2.5 | Communication Plan | bar: W2
2.6 | Data Governance Plan | bar: W2
3.0 | Integrated Customer Data | bar: W3 to W6
3.1 | POS Data Assessment | bar: W3
3.2 | E-commerce Data Assessment | bar: W3
3.3 | Loyalty Data Assessment | bar: W4
3.4 | Customer Identity Resolution | bar: W4 to W5
3.5 | Data Integration Pipeline | bar: W5 to W6
3.6 | Data Quality Validation | bar: W6
4.0 | Churn Prediction Solution | bar: W7 to W12
4.1 | Churn Definition | bar: W7
4.2 | Feature Engineering | bar: W7 to W8
4.3 | Model Development | bar: W8 to W10
4.4 | Model Validation | bar: W10 to W11
4.5 | Model Explainability | bar: W11
4.6 | Model Approval | bar: W12
5.0 | Customer Intelligence Dashboard | bar: W10 to W14
5.1 | Dashboard Requirements | bar: W10
5.2 | Dashboard Design | bar: W10 to W11
5.3 | Dashboard Development | bar: W11 to W13
5.4 | User Acceptance Testing | bar: W13
5.5 | User Training | bar: W13 to W14
6.0 | Retention Pilot | bar: W11 to W17
6.1 | Customer Segmentation | bar: W11
6.2 | Retention Intervention Design | bar: W12
6.3 | Control Group | bar: W13
6.4 | Pilot Launch | bar: W14
6.5 | Pilot Evaluation | bar: W17
7.0 | Operationalised Solution | bar: W17 to W19
7.1 | Production Deployment | bar: W17 to W18
7.2 | Monitoring Process | bar: W18
7.3 | Retraining Process | bar: W18
7.4 | Operational Handover | bar: W19
8.0 | Project Closure | bar: W19 to W20
8.1 | Final Evaluation | bar: W19
8.2 | Lessons Learned | bar: W20
8.3 | Final Documentation | bar: W20
8.4 | Sign-off | bar: W20
Legend:
Critical Path (0 float — any delay pushes project finish)
Non-Critical (has float / schedule buffer)
Phase summary bar