## Project Budget
AnalystLab Africa Consulting
Project Budget
Project: AI-Powered Customer Churn Prediction & Retention System : Tarrose Retail
Category | Line Item | Rate (R) | Unit | Quantity | Extended Cost (R)
Personnel | Project Manager -governance, delivery, phase-gate coordination | 18000 | per person-week | 10 | 180000
Personnel | Data Engineer -data assessment, integration pipeline, quality validation | 24000 | per person-week | 6 | 144000
Personnel | Data Scientist -model build, validation, segmentation, retraining design | 26000 | per person-week | 9 | 234000
Personnel Subtotal |  |  |  |  | 558000
Software Licences | Asana -project management (5 seats x 5 months) | 500 | seat-month | 25 | 12500
Software Licences | GitHub Team -source-controlled documentation & code | 600 | per month | 5 | 3000
Software Licences | BI Dashboard tool (e.g. Power BI Pro, 5 seats x 5 months) | 600 | seat-month | 25 | 15000
Software Licences | Misc. developer tooling / IDE licences | 5000 | lump sum | 1 | 5000
Software Licences Subtotal |  |  |  |  | 35500
Hardware | Peripherals / minor equipment upgrades (existing laptops retained) | 15000 | lump sum | 1 | 15000
Hardware Subtotal |  |  |  |  | 15000
Cloud Services | Cloud compute -model training & pipeline processing | 8000 | per month | 5 | 40000
Cloud Services | Cloud data warehouse / storage -unified customer dataset | 4000 | per month | 5 | 20000
Cloud Services | Dashboard hosting | 2000 | per month | 5 | 10000
Cloud Services | Data egress / networking | 10000 | lump sum | 1 | 10000
Cloud Services Subtotal |  |  |  |  | 80000
Training | Marketing & Customer Service dashboard training (materials + facilitation) | 20000 | lump sum | 1 | 20000
Training | Internal IT/Data team handover training (monitoring & retraining) | 15000 | lump sum | 1 | 15000
Training Subtotal |  |  |  |  | 35000
Estimated Project Subtotal (before contingency) |  |  |  |  | 723500
Contingency Rate |  |  |  |  | 10%
Contingency Reserve |  |  |  |  | 72350
TOTAL ESTIMATED PROJECT BUDGET |  |  |  |  | 795850
Comparison to Approved Charter Budget (Section 7)
Amount (R)
Approved Budget Ceiling (Charter Section 7, incl. 10% contingency) |  |  |  |  | 1000000
This Estimated Total Budget |  |  |  |  | 795850
Headroom vs. Approved Ceiling |  |  |  |  | 204150
Notes & Assumptions
• Tarrose Retail's own staff (IT Lead, Compliance Officer, Marketing & Customer Service Team, Internal IT/Data Team) are not costed here -their time is provided by the client, not billed against this consulting budget.
• Software, cloud and training line items are estimates for planning purposes; actual invoiced amounts should replace these once vendor quotes are confirmed.