## Project Schedule
AnalystLab Africa Consulting
Project Schedule
Project: AI-Powered Customer Churn Prediction & Retention System : Tarrose Retail
Activity ID | Activity Name | Duration (Working Days) | Start Date | Finish Date | Dependencies (Predecessor) | Assigned Resource
1.0 | Approved Project Foundation | 5 | 2026-08-10 | 2026-08-14 | — | Project Manager
1.1 | Project Charter | 1 | 2026-08-10 | 2026-08-10 | Start | Project Manager
1.2 | Business Case | 2 | 2026-08-10 | 2026-08-11 | 1.1 (SS) | Project Manager
1.3 | Stakeholder Requirements | 2 | 2026-08-11 | 2026-08-12 | 1.2 (FS) | Project Manager
1.4 | Project Objectives | 2 | 2026-08-13 | 2026-08-14 | 1.3 (FS) | Project Manager
2.0 | Approved Project Plan | 8 | 2026-08-12 | 2026-08-21 | — | Project Manager
2.1 | Scope Baseline | 3 | 2026-08-12 | 2026-08-14 | 1.3 (FS) | Project Manager
2.2 | Project Schedule | 2 | 2026-08-17 | 2026-08-18 | 2.1 (FS) | Project Manager
2.3 | Resource Plan | 3 | 2026-08-17 | 2026-08-19 | 2.2 (SS) | Project Manager
2.4 | Risk Plan | 3 | 2026-08-18 | 2026-08-20 | 2.2 (FS) | Project Manager
2.5 | Communication Plan | 3 | 2026-08-19 | 2026-08-21 | 2.3 (FS) | Project Manager
2.6 | Data Governance Plan | 3 | 2026-08-19 | 2026-08-21 | 2.5 (SS) | Compliance Officer
3.0 | Integrated Customer Data | 20 | 2026-08-24 | 2026-09-18 | — | Data Engineer
3.1 | POS Data Assessment | 3 | 2026-08-24 | 2026-08-26 | 2.0 (FS) | Data Engineer
3.2 | E-commerce Data Assessment | 3 | 2026-08-26 | 2026-08-28 | 3.1 (FS) | Data Engineer
3.3 | Loyalty Data Assessment | 3 | 2026-08-31 | 2026-09-02 | 3.2 (FS) | Data Engineer
3.4 | Customer Identity Resolution | 6 | 2026-09-02 | 2026-09-09 | 3.3 (FS) | Data Engineer
3.5 | Data Integration Pipeline | 6 | 2026-09-09 | 2026-09-16 | 3.4 (FS) | Data Engineer
3.6 | Data Quality Validation | 5 | 2026-09-14 | 2026-09-18 | 3.5 (SS+3d) | Data Engineer
4.0 | Churn Prediction Solution | 28 | 2026-09-21 | 2026-10-28 | — | Data Scientist
4.1 | Churn Definition | 3 | 2026-09-21 | 2026-09-23 | 3.0 (FS) | Data Scientist
4.2 | Feature Engineering | 8 | 2026-09-23 | 2026-10-02 | 4.1 (FS) | Data Scientist
4.3 | Model Development | 11 | 2026-10-02 | 2026-10-16 | 4.2 (FS) | Data Scientist
4.4 | Model Validation | 6 | 2026-10-16 | 2026-10-23 | 4.3 (FS) | Data Scientist
4.5 | Model Explainability | 3 | 2026-10-21 | 2026-10-23 | 4.4 (SS+lag) | Data Scientist
4.6 | Model Approval | 3 | 2026-10-26 | 2026-10-28 | 4.4, 4.5 (FS) | Sponsor (Head of Marketing & CX)
5.0 | Customer Intelligence Dashboard | 23 | 2026-10-12 | 2026-11-11 | — | IT Lead
5.1 | Dashboard Requirements | 3 | 2026-10-12 | 2026-10-14 | 4.2 (FS+lag) | IT Lead
5.2 | Dashboard Design | 6 | 2026-10-14 | 2026-10-21 | 5.1 (FS) | IT Lead
5.3 | Dashboard Development | 13 | 2026-10-21 | 2026-11-06 | 5.2 (FS) | IT Lead
5.4 | User Acceptance Testing | 3 | 2026-11-04 | 2026-11-06 | 5.3 (SS+lag) | Marketing & Customer Service Team
5.5 | User Training | 4 | 2026-11-06 | 2026-11-11 | 5.4 (FS) | Marketing & Customer Service Team
6.0 | Retention Pilot | 35 | 2026-10-19 | 2026-12-04 | — | Marketing & Customer Service Team
6.1 | Customer Segmentation | 3 | 2026-10-19 | 2026-10-21 | 4.3 (FS) | Data Scientist
6.2 | Retention Intervention Design | 3 | 2026-10-26 | 2026-10-28 | 6.1 (FS+lag) | Marketing & Customer Service Team
6.3 | Control Group | 3 | 2026-11-02 | 2026-11-04 | 6.2 (FS+lag) | Data Scientist
6.4 | Pilot Launch | 3 | 2026-11-09 | 2026-11-11 | 6.3 (FS+lag) | Marketing & Customer Service Team
6.5 | Pilot Evaluation | 3 | 2026-12-02 | 2026-12-04 | 6.4 (FS+lag) | Data Scientist
7.0 | Operationalised Solution | 15 | 2026-11-30 | 2026-12-18 | — | IT Lead
7.1 | Production Deployment | 8 | 2026-11-30 | 2026-12-09 | 4.6 (FS+lag) | IT Lead
7.2 | Monitoring Process | 3 | 2026-12-07 | 2026-12-09 | 7.1 (SS+lag) | IT Lead
7.3 | Retraining Process | 3 | 2026-12-09 | 2026-12-11 | 7.2 (FS) | Data Scientist
7.4 | Operational Handover | 5 | 2026-12-14 | 2026-12-18 | 7.3, 6.5 (FS+lag) | Tarrose Retail Internal IT/Data Team
8.0 | Project Closure | 5 | 2026-12-17 | 2026-12-23 | — | Project Manager
8.1 | Final Evaluation | 2 | 2026-12-17 | 2026-12-18 | 7.4 (SS+lag) | Project Manager
8.2 | Lessons Learned | 2 | 2026-12-21 | 2026-12-22 | 8.1 (FS+lag) | Project Manager
8.3 | Final Documentation | 2 | 2026-12-22 | 2026-12-23 | 8.2 (FS) | Project Manager
8.4 | Sign-off | 1 | 2026-12-23 | 2026-12-23 | 8.3 (FS) | Sponsor (Head of Marketing & CX)
Project Start |  |  | 2026-08-10
Project Finish |  |  | 2026-12-23
Total Calendar Duration (Weeks) |  |  | 19.3
Legend
• FS = Finish-to-Start (successor starts after predecessor finishes)
• SS = Start-to-Start (successor starts alongside predecessor)
• +Nd / +lag = successor start is offset from the predecessor by a gap (e.g. weekend, buffer, or observation window)
• Shaded rows (x.0) are phase summary rows — Start/Finish/Duration roll up automatically from their child activities (Duration = NETWORKDAYS, Mon–Fri)
• Dates and dependencies are carried forward from the approved Week 1 Work Breakdown Structure (09 Aug 2026 baseline)
Formulas:
Duration (Working Days) = NETWORKDAYS([Start Date],[Finish Date])
Start Date = MIN([Start Date, row below]:D11)
Finish Date = MAX([Finish Date, row below]:E11)

## Gantt Chart
AnalystLab Africa Consulting
Gantt Chart — AI-Powered Customer Churn Prediction & Retention System
Red bars = Critical Path (0 days float). Orange = Near-Critical (1-5 days float). Gold diamonds = milestones. See 'Project Schedule' tab for activity data and 'Critical Path Analysis' for float detail.