## Human Resources
AnalystLab Africa Consulting
Resource Allocation Plan
Project: AI-Powered Customer Churn Prediction & Retention System :Tarrose Retail
Human Respources
Role | Organisation | Allocation | Active Weeks | Key Responsibilities
Junior Project Manager | AnalystLab Africa Consulting | 100% throughout | Weeks 1–20 | Overall delivery, schedule and budget control, stakeholder communication, change control, phase-gate coordination
Data Engineer | AnalystLab Africa Consulting | 50%, tapering to 25% from Week 12 | Weeks 4–18 | POS/e-commerce/loyalty data assessment, identity resolution, integration pipeline, data quality validation, production support
Data Scientist | AnalystLab Africa Consulting | 75% | Weeks 7–18 | Churn model development, feature engineering, validation, explainability, segmentation, retraining process design
IT Lead | Tarrose Retail | 25%, rising to 50% in Weeks 17–19 | Weeks 1–19 | Systems access, technical review, dashboard build, production deployment, monitoring set-up
Compliance Officer | Tarrose Retail | As needed at phase gates | Ad hoc, incl. production readiness gate | POPIA sign-off on data handling, privacy review checkpoints
Marketing & Customer Service Team | Tarrose Retail | Light involvement | Weeks 11–17 | Dashboard requirements/UAT, segment validation, retention intervention design, pilot execution
Tarrose Retail Internal IT/Data Team | Tarrose Retail | Light involvement | Weeks 17–19 | Onboarding to monitoring & retraining process ahead of operational handover
Sponsor- Head of Marketing & CX | Tarrose Retail | Monthly steering + phase-gate reviews | Weeks 1–20 | Budget/scope sign-off, phase-gate approvals, full-rollout decision

## Software Resources
AnalystLab Africa Consulting
Resource Allocation Plan
Project: AI-Powered Customer Churn Prediction & Retention System : Tarrose Retail
Software Resources
Tool / Platform | Category | Purpose | Used By
Asana | Project Management | Task tracking, sprint/weekly work management (per Communication Plan) | Delivery Team, Project Manager
GitHub | Version Control / Documentation | Source-controlled documentation, model code, and pipeline scripts | Data Engineer, Data Scientist, IT Lead
Microsoft Excel | Reporting | Risk log, budget tracker, and schedule maintenance (per Communication Plan) | Project Manager
Python (pandas, scikit-learn) | Data Science / ML | Feature engineering, churn model development, validation | Data Scientist
SQL / Data Warehouse platform | Data Engineering | Unifying POS, e-commerce and loyalty data into a single customer view | Data Engineer
BI Dashboard tool (e.g. Power BI / Tableau) | Reporting | At-risk customer dashboard for Marketing & Customer Service | IT Lead, Marketing & CS Team
Team chat platform (e.g. Teams/Slack) | Communication | Daily/weekly stand-ups and blocker resolution (per Communication Plan) | All team members
Video conferencing platform (Zoom /Teams) | Communication | Steering committee meetings, working sessions, training | All stakeholders

## Hardware & External Services
AnalystLab Africa Consulting
Resource Allocation Plan
Project: AI-Powered Customer Churn Prediction & Retention System : Tarrose Retail
Hardware and external services required. Per the Charter, no external purchasing beyond existing tool licences is anticipated.
Hardware Resources
Services | Purpose | Provided By
Standard business laptops | Day-to-day work for all AnalystLab and Tarrose Retail team members | AnalystLab Africa Consulting / Tarrose Retail (existing)
Cloud compute (existing subscription) | Model training, pipeline processing, and dashboard hosting , no new on-premise hardware required | Tarrose Retail existing cloud provider
Secure VPN / network access | Data Engineer and IT Lead access to Tarrose Retail's POS, e-commerce and loyalty systems | Tarrose Retail IT
External Services
Service | Purpose | Notes
Existing cloud hosting provider | Hosts the production churn model and dashboard | Covered under Tarrose Retail's existing contract , no new procurement
POPIA legal/compliance advisory (as needed) | Escalation point if the internal Compliance Officer needs external legal input | Ad hoc only; not a standing engagement

## Team Responsibilities (RACI)
AnalystLab Africa Consulting
Resource Allocation Plan
Project: AI-Powered Customer Churn Prediction & Retention System : Tarrose Retail
R = Responsible · A = Accountable · C = Consulted · I = Informed, by project phase.
Team responsiblities
Phase | PM | Sponsor | Data Engineer | Data Scientist | IT Lead | Compliance Officer | Marketing & CS Team | Internal IT/Data Team
1.0 Project Foundation | A/R | C | I | I | I | C | I | I
2.0 Project Plan | A/R | C | C | C | C | C | I | I
3.0 Integrated Customer Data | A | I | R | C | C | I | I | I
4.0 Churn Prediction Solution | A | C | C | R | I | I | I | I
5.0 Customer Intelligence Dashboard | A | I | I | C | R | I | C | I
6.0 Retention Pilot | A | C | I | R | I | I | R | I
7.0 Operationalised Solution | A | C | C | C | R | R | I | R
8.0 Project Closure | A/R | R | C | C | C | I | I | I
Note: Accountable (A) sits with the Project Manager throughout, except deployment/handover (7.0, Compliance Officer signs off production readiness) and closure sign-off (8.0, Sponsor).